|  |  |
| --- | --- |
| DIA Urban Arts Projects | * Artwork fabrication in progress * Skyway columns site prep begins Feb. 25 * 34 artworks to be installed by March 31, 2017 * April Dedication Ceremony TBA |
| Courthouse Art Project | * Transfer of funds from reserves into the Art Trust Fund is complete * Project Overview – APPC March meeting * Convene first Art Selection Panel meeting TBA |
| Law and Liberty | * Seeking budget cost estimates for reinstallation of the two bronze figures in the new Duval county courthouse in progress |
| Water Street Parking Garage | * Artist Contract draft is currently under COJ review * The Design Proposal phase will be initiated following contract approval * Anticipated due date for Design Proposals is May 1, 2017 |
| Cuba Hunter Park | * Awaiting approved transfer of funds from reserves into Art Trust Fund * Project Overview – APPC March meeting * Art Selection Panel formation is in progress |
| Winton Drive | * Input has been received from CM Brown regarding scope of work * A site visit was completed in November * Project Overview – APPC March meeting * Art Selection Panel formation is in progress |
| Haskell Downtown Sculpture Initiative | * Fabrication of the sculpture for One Enterprise Center (Water/Hogan St.)   is in progress   * Fabrication for a second sculpture at Main/Adams Street is in progress * An Artist has been selected for a third sculpture at Laura/Forsyth. Site approvals by City Departments are in progress |
| Conservation and Maintenance | * Two comprehensive reports have been completed for city-owned public art and memorials * A Request for Proposals draft is in progress to identify an experienced conservator to complete maintenance and conservation needs identified in the reports * Anticipated Maintenance and Conservation work will begin summer of 2017 |
| Collections Management | * A 155-page appraisal report was completed in December for 23 city-owned artworks and memorials * The report is currently under review by the City’s Risk Management Division in order to add the 23 works to the existing APP collection |
| Liberty Street Artwork Removal | * In January, “The Memorial to the Great Fire” and the two bronze River Runners on the Northbank Riverwalk were deinstalled as a result of the COJ Liberty Street construction project. * The contractor was provided deinstallation, storage and resinstallation recommendations from APP. * The artworks will be reinstalled back in their original locations in 2018. |